## Scheduling-Burn down
Product: | Product A
Version: | v8.5.1 |  | Expected |  |  | Actual | [6 empty] | Expected | # Issues | Actual | # Issues
Id | Assigned To | Priority | Expected Start | Expected Finish | Hours | Actual Start | Actual Finish | Hours | Task Summary |  |  |  | Total Issues | 16 | Total Issues | 16
11608 | Dev A | immediate | 2012-02-24 | 2012-02-27 | 9 | 2012-02-27 15:30 | 2012-02-28 11:30 | 4 | Description A |  | 2012-02-20 | 2012-02-22 | 2012-02-20 | 15 | 2012-02-22 | 15
11581 | Dev A | immediate | 2012-02-27 | 2012-02-29 | 16 | 2012-02-21 09:30 | 2012-02-23 11:30 | 18 | Description B |  | 2012-02-22 | 2012-02-23 | 2012-02-22 | 14 | 2012-02-23 | 13
13567 | Dev B | immediate | 2012-02-20 | 2012-02-20 | 6 | 2012-02-21 09:30 | 2012-02-23 11:30 | 18 | Description C |  | 2012-02-27 | 2012-02-23 | 2012-02-27 | 11 | 2012-02-27 | 8
11646 | Dev C | immediate | 2012-02-23 | 2012-02-27 | 6 | 2012-02-22 09:00 | 2012-02-22 14:00 | 5 | etc |  | 2012-02-27 | 2012-02-27 | 2012-02-28 | 6 | 2012-02-28 | 3
13360 | Dev A | urgent | 2012-02-29 | 2012-03-02 | 20 | 2012-02-23 11:30 | 2012-02-27 15:30 | 20 | aqef |  | 2012-02-27 | 2012-02-27 | 2012-02-29 | 4 | 2012-02-29 | 2
13359 | Dev A | urgent | 2012-03-02 | 2012-03-05 | 4 | 2012-02-27 15:30 | 2012-02-28 11:30 | 4 | asdv |  | 2012-02-28 | 2012-02-27 | 2012-03-02 | 3 | 2012-03-01 | 0
13083 | Dev B | urgent | 2012-02-20 | 2012-02-22 | 16 | 2012-02-22 14:00 | 2012-02-27 10:00 | 20 | dafv |  | 2012-02-28 | 2012-02-27 | 2012-03-05 | 2
13574 | Dev C | urgent | 2012-02-27 | 2012-02-28 | 6 | 2012-02-22 14:00 | 2012-02-27 10:00 | 6 | dfv |  | 2012-02-28 | 2012-02-27 | 2012-03-06 | 1
13480 | Dev C | high | 2012-02-28 | 2012-02-28 | 2 | 2012-02-27 10:00 | 2012-02-28 12:00 | 12 | dafv |  | 2012-02-28 | 2012-02-28 | 2012-03-07 | 0
13211 | Dev C | high | 2012-02-28 | 2012-02-28 | 6 | 2012-02-28 12:00 | 2012-02-28 18:00 | 6 | asdfv |  | 2012-02-28 | 2012-02-28
13190 | Dev B | high | 2012-02-22 | 2012-02-27 | 20 | 2012-02-22 14:00 | 2012-02-27 10:00 | 20 | sadfv |  | 2012-02-29 | 2012-02-28
13514 | Dev A | normal | 2012-03-05 | 2012-03-06 | 10 | 2012-02-28 11:30 | 2012-02-29 13:30 | 10 | sdfv |  | 2012-02-29 | 2012-02-28
12042 | Dev A | normal | 2012-03-06 | 2012-03-07 | 8 | 2012-02-29 13:30 | 2012-03-01 13:30 | 8 | asdfv | asdfv | 2012-03-02 | 2012-02-28
13572 | Dev C | normal | 2012-02-29 | 2012-02-29 | 4 | 2012-02-29 08:00 | 2012-03-01 12:00 | 14 | sdfv | sdfv | 2012-03-05 | 2012-02-29
13485 | Dev B | normal | 2012-02-27 | 2012-02-28 | 8 | 2012-02-23 11:30 | 2012-02-27 15:30 | 20 | i8,kmum | i8,kmum | 2012-03-06 | 2012-03-01
13101 | Dev B | low | 2012-02-28 | 2012-02-28 | 2 | 2012-02-27 15:30 | 2012-02-28 11:30 | 4 | yumjyu | yumjyu | 2012-03-07 | 2012-03-01
|  |  |  | Total Effort Hours | 143 |  | Actual - Hours | 189
|  |  |  | Total Effort Man Days | 17.875 |  | Actual - Man days | 23.625
| Project/Version | Key dates
| Start date | 2012-02-20 |  | Effort Required and Available;
| Expected Completion | 2012-02-28 |  | Productivity factor | 15%
(last actual finish date) | Actual Completion | 2012-02-28 11:30 |  | Expected - Hours | 164.45
|  |  |  | Expected - Man days | 20.5562
|  |  |  | Hrs Available/wk | 110
|  |  |  | Weeks to complete | 1.495
|  |  |  | Work Days to complete | 7.475
How many hours do they work each day?
| Staff on this version; | Hours/Week | Can Start on; | Mon | Tue | Wed | Thu | Fri | Day Start | Day end
| Dev A | 40 | 2012-02-24 | 8 | 8 | 8 | 8 | 8 | 8:30 | 16:30
| Dev B | 40 | 2012-02-20 | 8 | 8 | 8 | 8 | 8 | 8:30 | 16:30
| Dev C | 30 | 2012-02-23 | 10 | 10 | 10 | 0 | 0 | 8:00 | 18:00
| Man Hrs/week | 110 |  | 26 | 26 | 26 | 16 | 16
Re-Calculate

## graph
2021-01-01 | 2012-02-22 14:00
2012-02-22 | 2012-02-23 11:30 | 2012-02-27
2012-02-27 | 2012-02-23 11:30 | 2012-02-29
2012-02-27 | 2012-02-27 10:00 | 2012-02-20
2012-02-27 | 2012-02-27 10:00 | 2012-02-27
2012-02-28 | 2012-02-27 10:00 | 2012-03-02
2012-02-28 | 2012-02-27 15:30 | 2012-03-05
2012-02-28 | 2012-02-27 15:30 | 2012-02-22
2012-02-28 | 2012-02-28 11:30 | 2012-02-28
2012-02-28 | 2012-02-28 11:30 | 2012-02-28
2012-02-29 | 2012-02-28 11:30 | 2012-02-28
2012-02-29 | 2012-02-28 12:00 | 2012-02-27
2012-03-02 | 2012-02-28 18:00 | 2012-03-06
2012-03-05 | 2012-02-29 13:30 | 2012-03-07
2012-03-06 | 2012-03-01 12:00 | 2012-02-29
2012-03-07 | 2012-03-01 13:30 | 2012-02-28
2012-02-28

## Product A - v8.5.1
Product: | Product A
Version: | v8.5.1 |  | Expected |  |  | Actual
Id | Assigned To | Priority | Expected Start | Expected Finish | Hours | Actual Start | Actual Finish | Hours | Task Summary
11608 | Dev A | immediate | 2012-02-24 |  | 9 |  |  |  | Description A |  | 0 | 2012-02-25 | 2012-02-24
11581 | Dev A | immediate |  |  | 16 |  |  |  | Description B |  | 0 | 1
13567 | Dev B | immediate | 2012-02-27 |  | 6 |  |  |  | Description C |  | 0 | 2012-02-28 | 2012-02-27
11646 | Dev C | immediate | 2012-02-20 |  | 6 |  |  |  | etc |  | 0 | 2012-02-21 | 2012-02-20
13360 | Dev A | urgent |  |  | 20 |  |  |  | aqef |  |  | 1
13359 | Dev A | urgent |  |  | 4 |  |  |  | asdv |  | 0 | 1
13083 | Dev B | urgent |  |  | 16 |  |  |  | dafv |  | 0 | 1
13574 | Dev C | urgent |  |  | 6 |  |  |  | dfv |  | 0 | 1
13480 | Dev C | high |  |  | 2 |  |  |  | dafv |  | 0 | 1
13211 | Dev C | high |  |  | 6 |  |  |  | asdfv |  | 0 | 1
13190 | Dev B | high |  |  | 20 |  |  |  | sadfv |  | 0 | 1
13514 | Dev A | normal |  |  | 10 |  |  |  | sdfv |  | 0 | 1
12042 | Dev A | normal |  |  | 8 |  |  |  | asdfv | asdfv | 0 | 1
13572 | Dev C | normal |  |  | 4 |  |  |  | sdfv | sdfv
13485 | Dev B | normal |  |  | 8 |  |  |  | i8,kmum | i8,kmum
13101 | Dev B | low |  |  | 2 |  |  |  | yumjyu | yumjyu
|  |  |  | Total Effort Hours | 143 |  | Actual - Hours | 0
|  |  |  | Total Effort Man Days | 17.875 |  | Actual - Man days | 0
| Project/Version | Key dates
| Start date | 2012-02-20 |  | Effort Required and Available;
| Expected Completion |  |  | Productivity factor | 15%
(last actual finish date) | Actual Completion |  |  | Expected - Hours | 164.45
|  |  |  | Expected - Man days | 20.5562
|  |  |  | Hrs Available/wk | 112
|  |  |  | Weeks to complete | 1.4683
|  |  |  | Work Days to complete | 7.3415
How many hours do they work each day?
| Staff on this version; | Hours/Week | Can Start on; | Mon | Tue | Wed | Thu | Fri | Day Start | Day end
| Dev A | 42 | 2012-02-24 | 9 | 8 | 8 | 8 | 9 | 8:30 | 17:30
| Dev B | 40 | 2012-02-27 | 8 | 8 | 8 | 8 | 8 | 8:30 | 16:30
| Dev C | 30 | 2012-02-20 | 10 | 10 | 10 | 0 | 0 | 8:00 | 18:00
| Man Hrs/week | 112 |  | 27 | 26 | 26 | 16 | 17
Notes:
1. Blue cells are ones the users will enter data into.
2. Green cells are the ones you must calculate.
3. The user will enter the task details and complete the blue cells.
4. The spreadsheet will calculate the cell values in the green cells.
Constraints - Make sure calculations comply with these;
1. A person cannot be working on more than one task at the same time.
2. Tasks must be done/scheduled in the Priority order, ie Tasks are done by each assigned person in order Immediate down to Low.
3. Work cannot be started or finished on days the person is not working – so not on Saturday or Sunday, or on week days when they are not working.
4. Work cannot be started or finished outside the work hours. The workday starts at the time indicated for each developer and work should not be scheduled to start or finish after their day is due to end, ie an 8hour day start at 0830 would finish at 0530. So any task which is calculated to be complete at 1830 on a day, would in fact not be completed until 0930 the next day.
Button 1

## Sheet1
2012-02-24 | 2012-02-24 | 2012-02-24 | 2012-02-24
2012-02-27 | 2012-02-27 | 2012-02-27 | 2012-02-27
2012-02-27 | 2012-02-27 | 2012-02-27 | 2012-02-27
2012-02-20 | 2012-02-20 | 2012-02-20 | 2012-02-20
2012-02-28 | 2012-03-01 | 2012-02-28 | 2012-03-01
2012-03-01 | 2012-03-02 | 2012-03-01 | 2012-03-01
2012-02-27 | 2012-02-29 | 2012-02-27 | 2012-02-29
2012-02-20 | 2012-02-21 | 2012-02-20 | 2012-02-20
2012-02-21 | 2012-02-22 | 2012-02-21 | 2012-02-21
2012-02-22 | 2012-02-28 | 2012-02-21 | 2012-02-22
2012-02-29 | 2012-03-05 | 2012-02-29 | 2012-03-05
2012-03-02 | 2012-03-05 | 2012-03-02 | 2012-03-05
2012-03-05 | 2012-03-06 | 2012-03-05 | 2012-03-06
2012-02-28 | 2012-02-29 | 2012-02-22 | 2012-02-22
2012-03-05 | 2012-03-06 | 2012-03-05 | 2012-03-06
2012-03-06 | 2012-03-06 | 2012-03-06 | 2012-03-06